## Payment Schedule
Payment Schedule
| PROJECT | RUTHERFORD INDUSTRIAL UNITS |  |  |  | PROGRESS CLAIM | 04
| PROJECT ADDRESS | 9 MIRAGE ROAD, RUTHERFORD |  |  |  | INV NO | INVXXXX
| CLAIMANT | ROGERS CONSTRUCTION GROUP (56 615 190 157) |  |  |  | DATE RECEIVED | 2024-08-29
| SCOPE | MAIN CONTRACT WORKS |  |  |  | PERIOD | AUG24
This is a payment schedule made under the Building & Construction Industry Security of Payment Act 1999 (NSW)
CONTRACT SUMMARY
| ORIGINAL CONTRACT SUM |  | TOTAL LET ($) | COMPLETED TO DATE |  | LESS PRIOR ($) | THIS CLAIM ($)
|  |  |  | (%) | ($)
1 | Preliminaries, Overheads & Margin |  | 5000 | 100% | 5000 | 5000 | 0
2 | Architectural |  | 5000 | 100% | 5000 | 5000 | 0
3 | Structural Engineer |  | 5000 | 100% | 5000 | 5000 | 0
4 | Traffic Engineer |  | 5000 | 100% | 5000 | 5000 | 0
5 | Hydraulic Engineer |  | 5000 | 100% | 5000 | 5000 | 0
6 | BCA Consultant / Other |  | 5000 | 60% | 3000 | 0 | 3000
7 | Geotechnical Engineer |  | 5000 | 60% | 3000 | 0 | 3000
8 | Fire Engineer |  | 5000 | 60% | 3000 | 0 | 3000
| SUB TOTAL ($) |  | 40000 | 85% | 34000 | 25000 | 9000
| VARIATIONS |  | APPROVED ($) | COMPLETED TO DATE |  | LESS PRIOR ($) | THIS CLAIM ($)
|  |  |  | (%) | ($)
| V01 - Variation 1 |  | 1000 | 100% | 1000 | 1000 | 0
| V02 - Variation 2 |  | 500 | 100% | 500 | 500 | 0
| V03 - Variation 3 |  | 500 | 100% | 500 | 500 | 0
| SUB TOTAL ($) |  | 2000 |  | 2000 | 2000 | 0
| ADJUSTED CONTRACT SUM |  | TOTAL ($) | COMPLETED TO DATE |  | LESS PRIOR ($) | THIS CLAIM ($)
|  |  |  | (%) | ($)
| TOTAL (EXC GST) |  | 42000 | 85.71% | 36000 | 27000 | 9000
[6 empty] | TOTAL (EXC GST) | 9000
| Superintenent Approval |  |  |  |  | GST ($) | 900
[6 empty] | TOTAL (INC GST) | 9900
|  | Ben Clifton |  | 2024-09-04
|  | Engine Room |  | Date
PAYMENT LIST
| PERIOD | CLAIM | INVOICE NO | INVOICE DATE | VALUE ($) | GST ($) | VALUE ($)
| MAY24 | 01 | 2546 | 2024-05-29 | 10000 | 1000 | 11000
| JUN24 | 02 | 2666 | 2024-06-30 | 1000 | 100 | 1100
| JUL24 | 03 | 2691 | 2024-07-31 | 1000 | 100 | 1100
| AUG24 | 04 |  |  | 0 | 0 | 0
| SEP24 | 05 |  |  | 0 | 0 | 0
| OCT24 | 06 |  |  | 0 | 0 | 0
| NOV24 | 07 |  |  | 0 | 0 | 0
| DEC24 | 08 |  |  | 0 | 0 | 0
| TOTAL |  |  |  | 12000 | 1200 | 13200